## Sheet1
| STATUS | TASKS - DUE DATES | Completed = GREEN | comments
22.Permanantly Deleting YourKnow Content This is not functional. We need the ability to clear deleted content and associated links from the database and directories. | completed but needs to be verified | Needs to be verified
24. ADD "Just Me" Menu selection, page DESIGN and FUNCTIONALITY under " My YourKnow" Use image page: http://yourknow.com/design/JustMeEdit.php and https://www.screencast.com/t/Tw9kdpszSxC7 | 80% Complete
38. UPLOADING and eReader ISSUES: Upload file types (epub, pdf, .pptx .rtf, .doc, excel) Max file size = 50MB UPLOAD test Results: ***FILE UPLOAD Feedback*** 1. All Upload formats seem to be working *except for (.pptx)* this needs fixing. Note: the old ..PowerPoint format is working though. 2. File sizes greater than *15 MB* is an ISSUE Except for PDF (PDF is fully functional) : Uploading large file sizes seem to be the issue: a. Invalid PDF Structure for about an hour, and then the ebook appears b. Missing thumbnail cover c. Page turning is *super slow*. ..everything was slow, even accessing the eBook Menu tool bar NOTE: I uploaded a 16MB epub file and got an “invalid PDF structure” after the upload was complete. However, I checked after an hour and the 16MB epub book was there. 3. Upload Date tends to be pointing to an incorrect time zone. It should be reflected in the User's time zone (I uploaded a book 10/8/18 and it tagged the upload as 10/9/18) | 90% complete- these are fixes and optimization
39. Alert Notification on “My Interests” : *Cron*: (1). Cron job is once a week, ..on Sundays - (for books accessed over a 7 day period) -top 5 count per Category *User*: (2). The “User” must have logged more than *10* reads in that specific “Book category” to qualify for a book alert that maps to that “Category" *Book*: Qualifying a book for alerts: (3). If a book is in "Education", for it to be in the "distribution" pool to push an alert to “interested” members: - It must be read/accessed by YourKnow users (sign-in and non sign-in) a minimum of 50 times (4). In EACH Category, the book must be in the top 5 ranking of books accessed over a 7 day period. No repeat alert notifications for the same book (5). *Notifications*: per *Category* Pick the top #1 book out of the top 5 per category, NOTE: if the book was sent out previously, then choose the second one, ..if the second book was sent out previously then move to the third, etc.. if all of the top 5 books were sent out, then no new alerts for that category. In Theory: Users can recieve up to 16 notifications per week, if they select ALL of YourKnow Categories. That would amount to the *chosen* book in each Category | Cron Job is 75% complete
40. Highlighting Reading and Sticky Notes Content functionality: Users/Publishers should be able to create highlight/unhighlight and sticky note/unsticky note) any section of a book and store those atributes. The area will be highlighted in yellow. (b). Add eReader - single page option to eReader menu tool bar
Collaboration Issues: 4.. "Publish to YourKnow" during Live Collaboration: The" Publish to YourKnow" files function: (FROM both the "Live-Collaboration" and "Files TAB") gives an error when you try to publish to YourKnow. Feedback: FILES TAB: -(using PUB ID) 1. Publish is not working in Files TAB Note: This is the same Publisher “Upload to YourKnow” page (Ref#38). The only difference is that it is doing an initial capturning of the file for the Publisher/User to upload and publish. Currently it just hangs in uploading mode and becomes unresponsive (a). Also the Custom Image file option is missing from the Upload/Publish window (b). Also I noticed that ISBN is marked (*), ..it is not a required filed. (let’s simply remove that (*) for all Publisher Upload Windows -**besides, there is no existing validation on that field ..just remove the "*" 4. Live Collaboration mode: (Using PUB ID) 1. Publish is not working in Live Collaboration a. Files uploaded (example, .docx, pdf, etc) and ready for Publish to YourKnow: Currently it just hangs in uploading mode and becomes unresponsive b. YK -Writing pad files (yk) ready for Publish to YourKnow: Currently it just hangs in uploading mode and becomes unresponsive 8. In “Continued Collaboration” (CC) and “Files” TAB - the download file option has stopped working - check to see if file-download is broken across the site. Feedback: Download works for files in Files TAB except the *.yk* writing pad file type, ..which are just rf files created in the Writing PAD(. ..that one still gives a 404 error. ) I cannot test the Continued Collaboration CC portion yet (not to ne confused with New Collaboration NC), because the CC option is not worknig at the moment for the select Event CC. Once the CC option is working and .yk (rtf-) file type is resolved.. we will be able to test and close this 9. The EDIT file in New Collaboration (NC) and Continued Collaboration (CC) does not work. It should drop the file into the writing pad for editing if the file is doc,docx rtf, or yk - yourknow file 10. Unable to test the Publish to yourknow option at the moment. This function (see #38) needs to be operational before I can test. 14. LIVE Collaboration “Copy and paste” is not working in the writing pad. The system is not recording-sharing copy -paste text. - verify and fix 15. Collaboration “live writing” (writing pad) seems to be slow (lag time) for other users to see the live content. this needs to be optimized. Users/attendees should see “live” keystrokes - Very important optimization issue 16. Needs Review Writing pad Guest/invitees time out : I paused the collaboration for 10 mins, and when I returned, the members could not see what I was writing in the writing pad. I had to “pass the Pen” to a member to actually re-engage communication. Solution: We should make sure that the screen-refresh and connectivity stay on. Please test this out. 17. FOR Live Collaborations: MEMBERS' access to “current” or “uploaded” files in a LIVE collaboration should be as follows: “Download” and “Delete” options if that user uploaded the file(s) to the Live Collaboration “Download” only for all other files (from other members) Note: Admin will have full options (this is currently working) | 75% Complete
43. ALL website pages need to be Responsive: Responsiveness for Mobile Devices and brower Compatibility (Safari,Chrome, IE) (b) Revise “content and layout“ for About YourKnow” page.
45. Final SITE TEST (INCLUDING CHECKING THE REGISTRATION PROCESS, NOTIFICATION, UPLOADING AND COLLABORATION) Migrate site into PRODUCTION | Final Testing- Prod
46. QUICK FIXES and Improvements:- (relation to #44) (a). Alert Function for *Event Update* and *Continued Collaboration (CC)*- If you *Update an Event* or Create a *New Event* using the *Continued Collaboration* (CC) Function. The Event updates and CC Alerts are not triggered. No alerts are sent out (the Updated or CC alerts are not being sent) ....The alerts are currently only sent out for "New Collaboration" (NC) (b). The Live Colaboration Writing Pad: Auto refresh for file names/changes and updates is not working properly. The live page should continiously refresh (c). In a Continued Collaboration (CC): Both the original Event Creator and the Group admin should be able to create a CC Event. Currently only the original Event Creator can create a CC Event. (d). Continued Collaboration (CC)- When a live CC has ended, There needs to be a “Collaboration has Ended” notification (e). IPAD and Mobile Device Touch Issue: Right click with iPad and other mobile devices… this needs to work (on the Files TAB, a user with an ipad or Mobile device, the User needs to have the “Right Click” and touch screen/swipe screen enabled... suggestion is to use a "hover over" to facilitate right click functions. ..similar to displaying "book info" when the cursor is over a book image **NOTE :(we may be able to solve with the "hover-over" to show- right click options) (f). Upload files: Files Tab, if you “double click” on a file from your local computer to upload from your computer directory, the system does not recognize that command and will not place the file in the YourKnow Group files listing (g). eBook: Page turning (eReader) is not working well on an iPad and mobile devices. This needs to be fixed (did you install the new zip version of eBook? I sent zip file previously) (h). Files TAB and Live Collaboration: Downloading files Created in the “Writing pad” (yk-format) is not working, it produces a “page error”. . Make sure that the (yk) files can also be downloaded in a Live Collaboration setting. NOTE: ("uploaded" files are ok when downloaded from the files TAB or Live Collaboration setting) (j). Avatar: The On-line green dot does not seem to be fully functional. It should be green when a User/Publisher is signed into YourKnow, and grey when they sign out. Also, the "Default Avatar Image" for User's/Publishers should be the "First" Letters of the User/Publisher's full name (e.g, for Jeff Kline, the Avatar will show "JF") From Members TAB: Design tweaks for Avatar pop-up (member info) 1. The design needs to show avatar info when the cursor hovers over the image on the Members tab (similar to homepage hover over and pop-up) 2a. The pop-up design needs improvement. See image https://www.screencast.com/t/jx6PyWDjy 2b. The Avatar pop-up needs an “alert notification” button/icon to “push” an alert message to that specific User. It is an alert that allows another menber to send a notification “message” to another member. The alert message (25 char max) goes into the user’s alert box, with an “x” to delete the alert. Note: this does not go to a pop-up page, it is simply a "personal" alert notification. Alert bell Format is : <Avatar>: Message: <text message> <remove="x"> (n). From Homepage: the Groups pages need to show a larger and standard size transparent image (see current production Groups transparent background-pages as an example). This applies to signed-in and non-signed in pages. We should set a standard number of rows before scrolling bar is enabled (say 9 or 11 rows) , and if the List has only 4 rows, the we show just that, but keep the page size/height and footer consistent for all pages. We just need to keep the page size and footer consistent See image https://www.screencast.com/t/1gQthzDt (x). Time Zone needs to be adjusted for Users : see image https://www.screencast.com/t/b5Dl3fxLF . .. this is not working properly. SEE feedback Image: https://www.screencast.com/t/fR5w7Fo6zZo .. This is not working properly. the Time Zone "location recognition" portion is missing. Example: If I create an event for 8:00AM PDT and Travel to EDT time zone, the alert notification bell and calendar "Event time" is not adjusting for the new time zone. **(We can test together) (z). The Collaboration option- OFF-LINE Collaboration (OF) process has stopped working since the migration: Currently it puts the Event in the “alert bell” and “Event calendar”, however it does not link to the detailed pop-up page that provides details on the off-line meeting ..The Alert bell notification does not produce any action nor link to the meeting details pop-up page How it “should” work: From the Calendar TAB, the user creates an Off-Line (OF) Collaboration Event, and Invites group members (z.1). The (OF) collaboration will send out an “Event invite” and "Event Reminder" to Members’ alert bell (it will also show up on their Event Calendar. (similar to our current process). (z.2). IF the user clicks on the (OF) invite in their alert bell, they will be taken to a pop-up page that has all of the Off-Line (OF) meeting details, including: “Event Title”, “Description”, “Start date/time”. “End date" and "End time”, “Invitees” and "Meeting Location”. *NOTE: This pop-up meeting info will have a “close” button. (z.3). This event invite works just like ALL the other Invite alerts, however this one leads to just a pop-up with all of the event details (z.4). if the (OF) event expires, and the user clicks on it, the pop-up would display the pop-up meeting details once and then be removed from the alert count-list (similar to our current process). (z.5). If the event is in the future it will remain in the alert until the meeting actually begins (similar to our current process). (A1). Forgot Password process is not working, and the password recovery page need the correct look and feel - Verify and Tweak if needed (A2). Sign-in Blinking Cursor : When a user clicks on Sign-in, It should take the user to the login page, when the blinking cursor is “automatically” inserted into the Username/email login field (A3). Design tweaks 1. See image : https://www.screencast.com/t/mBEFl0yond 2. See image : https://www.screencast.com/t/ReCHIen8A 3. See image : https://www.screencast.com/t/GUgy8NQGfDpb 4. See image : https://www.screencast.com/t/fcC1YlhB2 5. See image : https://www.screencast.com/t/7DJrl1bDv 6. See image : https://www.screencast.com/t/o3NCq1tT9 7. See image : https://www.screencast.com/t/5DjHdNTgv 8. See image : https://www.screencast.com/t/oJxjEqJTcR | 75% in this list are tweaks and improvement related issues (meaning development is done) and 25% feature completion
47. The IM is not working properly for Members in a LIVE Collaboration. Revised detailed Feedback: This is an issue that happens 80% of the time.. needs to be stable. 1. In a live Collaboration, if a Member/invitee decides to post the “first” IM -message, the IM window becomes unresponsive and the user is unable to post. It currently only works If the Event Creator or Admin posts the “first” IM-message, then all other users are able to post to the IM, OR if the User is initially assigned the Pen. Solution:**Any User/Invitee/Event creator should be able to post the "first" IM-message. ..consistently | This is fully functional - there are a few glitches that need to be fixed
Mobile APP Development - Tasks - Design- Development
37. Please attend to these new issues. (high importance) - I will add them to the task list. Please see production version for guidance if needed. *Critical Collaboration ISSUES*1. Create an Event - Event Title: Event titles are UNIQUE, However the system is not allowing the creation of a New Collaboration (NC) - The error message is the “Event Title already exists” ..even when the event title is clearly new and unique + However, when you check out the events list, the collaboration seems to be there.2. Create new collaboration: Selecting group members to add to your Collaboration. a. We need to remove old and unsubscribed members from the drop down selection list . Currently they remain there b. We need to be able to select and deselect group invitees from the dropdown list. Currently this is not working.3. Also Continued Collaboration(CC) does not seem to work. When working properly -> It should take an expired collaboration and transfers all records, members, files, etc. to create a new collaboration (NC)- with a date stamp added to the title. (See production version) + Also, if you choose a future date for a collaboration the calendar does not show the future collaboration (count-indicator) 4. Off-line (OF) Collaboration do not seem to work either. (See production version)5. Important: Only the Event creator/initiator (a group member) AND also the Group Admin can START the Collaboration. *Everyone else will have a “Wait” screen. When the Collaboration “creator/initiator of Group Admin starts the collaboration. ..all waiting members will be taken into the collaboration workspace then.