## Issues
ID | Priority | Issue | Status | Type | Category | Issue DateTime | Last Update | Screenshot | Comments
1 |  | Two Factor Autenthication for Admin page | New |  | Admin |  | 6/11/2019 2:25AM
2 |  | Group Information Popup: Date/Time format should be more readible. Use YYYY-MM-DD HH:mm:ss | New |  | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/OyOtySmeE
3 |  | Group Information Popup: "Last Accessed" datetime is missing | New |  | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/OyOtySmeE
4 |  | Cron job didn't send any "Suggested Reading" alerts | New |  | Backend |  | 6/11/2019 2:25AM
5 |  | Writing pad is NOT updating/refresing with the new content for invitees consistently. Users are sometimes forced to refresh their browser. Repro steps aren't always consistent and it may happen with more than 2 users at a time. | New |  | Web |  | 6/11/2019 2:25AM
6 |  | File uploads refresh is not working properly for "Event Creator". After the first 2 files upload in a Live Collaboration (NC and CC), the files refresh stops working for Event creator. | New |  | Web |  | 6/11/2019 2:25AM
7 |  | Changing file permissions in a live collaboration is functional, but not refreshing the changes on other invitees sessions.Only files with the permission "All Group Members" will show on the Files TAB. If a file has the permission of Invitees Only, it will remain in the collaboration session but not be available to the rest of the group if they weren't involved in the session. If the live collaboration files permission is changed during the live collaboration to "All Group Members", then that file will appear visible and downloadable in the groups "Files" tab. | New |  | Web |  | 6/11/2019 2:25AM
8 |  | When you upload a file to a live collaboration, the current live collaboration switches to the newly uploaded file instead of staying on the file already being edited. The system should simply upload the file and allow users to continue working on the file in the writing pad before the upload occured. | New |  | Web |  | 6/11/2019 2:25AM
9 |  | REGRESSION: File arrangement issues showing on the files tab. | New | Bug | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/ot15oqFmDmM
10 |  | Need to be able to edit uploaded files of type DOC, DOCX, RTF, EPUB | New |  | Web |  | 6/11/2019 2:25AM
11 |  | Writing pad screen should expand to take up any unused space in the browser. This also applies to NC, CC and Just me. | New |  | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/yCuEIJVZFuj
12 |  | eReader is slow for initial book access. Book sizes need to be compressed and the process optimized. | New |  | Web |  | 6/11/2019 2:25AM
13 |  | New and updated event collaboration emails should come from "YourKnow Notification <notification@yourknow.com>". This is not going out as expected. Comes from info@yourknow.com with a subject of "YourKnow Invite for 06/06/2019 2:43 PM" | New |  | Backend |  | 6/11/2019 2:25AM
14 |  | Book reader portrait view: on mobile web doesn't show whole book even in full-screen mode. Users have to scroll to see whole page. 1. Open Chrome 2. Navigate to YourKnow.com 3. Click on the first book in the list | New |  | Mobile Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/27EOqFT3
15 |  | Book reader portrait view: icons are too large and take up a lot of screen real-estate. | New |  | Mobile Web |  | 6/11/2019 2:25AM | http://www.screencast.com/t/5uUDTLR4blhD
16 |  | Book reader landscape view: when you flip to the second page of the book, you see both pages are fitting on the screen but you have to be very precise with where you scroll and not actually scroll within the book itself but near the icons to scroll the whole page. | New |  | Mobile Web |  | 6/11/2019 2:25AM | http://www.screencast.com/t/UPO5jklYr
17 |  | URL links need to work in the writing pad. Currently if you paste a URL into the writing pad it is not working. | New |  | Web |  | 6/11/2019 2:25AM
18 |  | Links in writing pad should launch a smaller and seperate browser pop-up window to show URL content | New |  | Web |  | 6/11/2019 2:25AM
19 |  | Search bar is misaligned see image | Complete |  | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/F80c46YV
20 |  | Update writing pad to add math formulas (see open source plug-ins http://visualmatheditor.equatheque.net/site/download.html OR http://www.sagemath.org ). math component would be enabled by adding a "math" button in writing pad menu. | New |  | Web |  | 6/11/2019 2:25AM
21 |  | Issue with some book uploads and not others. Need some type of error checking and better error handling to not display below error to user. 1. Open Browser 2. Navigate to https://yourknow.com 3. Sign In 4. Click My YourKnow > Just Me 5. Click Upload File 6. Choose book of type EPUB 7. Click on book and choose Publish to YourKnow 8. Fill out form and click Upload 9. Book should upload correctly |  | Bug | Web |  | 6/11/2019 2:25AM |  | Received 2 different responses for this. On 2 books it worked just fine. On the third I got the below error on the Upload to YourKnow page. A PHP Error was encountered Severity: Warning Message: copy(./uploads/files/American-Sniper---The-Autobiography-of-the-Most-Lethal-Sniper-in-U-S--Military-History---Chris-Kyle-): failed to open stream: No such file or directory Filename: front/Upload.php Line Number: 2999 Backtrace: File: /var/www/html/application/controllers/front/Upload.php Line: 2999 Function: copy File: /var/www/html/index.php Line: 637 Function: require_once 1754aoutfile20190606100604000000.
22 |  | Show publisher name in the invite members dialog | Complete | Bug | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/pVJAgN6kx
23 |  | Create instructions for github setup for code and data storage and backup access | New | Documentation | Backend |  | 6/11/2019 2:25AM
24 |  | Document backup/restore process | New | Documentation | Backend |  | 6/11/2019 2:25AM
25 |  | Create or add open-source blog module. Module should use YourKnow security to get commentors to sign up for YourKnow account. Blog posts and administration tasks should be managed via the YourKnow admin module. | New | Feature | Web |  | 6/11/2019 2:25AM
26 |  | Whisper functionality should work from both the discussion and members tabs within a collaboration | Complete |  | Web |  | 6/11/2019 2:25AM
27 |  | Make email addresses for YourKnow notifications consistent. Email address should be notification@yourknow.com | New |  | Backend |  | 6/11/2019 2:25AM | https://www.screencast.com/t/PRTN0pAUa
28 |  | Responsive issues on all mobile browsers. Mantra wording showing BEHIND the search bar. | Complete | Bug | Mobile Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/eIv3Rgmrot1
29 |  | Search bar is misalignedin Safari | New | Bug | Mobile Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/F80c46YV
30 |  | "START EVENT" and "EVENT NOT STARTED" pages For these two pages we need to display all of the following information : Event Name : < event_name> : <Date> : <Time> : Group <group_name> | New |  | Web |  | 6/11/2019 2:25AM
31 |  | "START EVENT" and "EVENT NOT STARTED" pages For these two pages we need to display all of the following information : Event Name : < event_name> : <Date> : <Time> : Group <group_name> | New |  | Mobile |  | 6/11/2019 2:25AM
32 |  | Under "My YourKnow", add a roll-up calendar titled "My Calendar" to show all events for the logged n user | New | Feature | Web |  | 6/11/2019 2:25AM
33 |  | Add calendar icon with list of all upcoming events next to bell icon | New | Feature | Mobile |  | 6/11/2019 2:25AM
34 |  | When creating a new event, the pop-up "create new event" window remains displayed for a long time before closing. Should close on submit and display some icon showing that it is processing the request. | New |  | Web |  | 6/11/2019 2:25AM
35 |  | Add the current Group Name and menu tabs to the live Collaborations pages (NC, CC) asas well as (OF) -Offline | New |  | Web |  | 6/11/2019 2:25AM | https://www.screencast.com/t/ZapsFBRn7X
36 |  | For live collaboration events, add an icon to get back into the collaboration if the user backed out to the main group screens | New |  | Web |  | 6/11/2019 2:25AM
37 |  | Rebuild writing pad to give better functionality and maintenance | New | Feature | Web |  | 6/11/2019 2:25AM
38 |  | The pen seems to lose previous assignment on certain mobile toggles | New | Bug | Web |  | 6/11/2019 2:25AM
39 |  | Mobile pop-up notifications are not working properly. Many users are not receiving the Event notifications. Event Notifications only showing up in the alert bell or some users. | New |  | Mobile |  | 6/11/2019 2:25AM
40 |  | If you access the collaboration from the alert bell, the navigation workflow takes you back to the notification list if you toggle out of a live collaboration instead of going into the main collaboration screen. | New |  | Web |  | 6/11/2019 2:25AM
41 |  | Need a select all delete/clear all for notifications | New | Feature | Web |  | 6/11/2019 2:25AM
42 |  | If your mobile device screen goes on idle for a moment, when you open and return to the collaboration it stops receiving writing updates and changes | New | Bug | Mobile |  | 6/11/2019 2:25AM
43 |  | Writing pad update delay is a bit too long. Should update every 3 seconds. | New |  | Web |  | 6/11/2019 2:25AM
44 |  | Verify "Forget password" process may not be working correctly on mobile. | New |  | Mobile |  | 6/11/2019 2:25AM
45 |  | Use a forget password image/link with YourKnow logo. | New |  | Web |  | 6/11/2019 2:25AM
46 |  | Use a forget password image/link with YourKnow logo. | New |  | Mobile |  | 6/11/2019 2:25AM
47 |  | eReader: Add a small bookmark indicator on the page, so that the reader can be reminded which page is actually bookmarked. | New | Feature | Web |  | 6/11/2019 2:25AM
48 |  | eReader: Add a small bookmark indicator on the page, so that the reader can be reminded which page is actually bookmarked. | New | Feature | Mobile |  | 6/11/2019 2:25AM
49 |  | Ending a collaboration changes the screen size, it now zooms in. The screen size should remain the same. | New |  | Web |  | 6/11/2019 2:25AM
50 |  | On the Invite members screen, make the (+) blue | New |  | Web |  | 6/11/2019 2:25AM
51 |  | On the Invite members screen, if a member tries to invite a person again, there should be a pop-up saying invite already sent | New |  | Web |  | 6/11/2019 2:25AM
52 |  | Accept/decline invite icons are too close together. Need additional separation. | New |  | Web |  | 6/11/2019 2:25AM
53 |  | On the Discussion TAB, the keyboard takes over the entire space and the user has no idea of their typing process. | New |  | Web |  | 6/11/2019 2:25AM
54 |  | On the files tab, change file folders on the left side to blue | New |  | Web |  | 6/11/2019 2:25AM
55 |  | Writing pad needs spell check process | New |  | Web |  | 6/11/2019 2:25AM
56 |  | Chat indicator needed during live collaborations | New |  | Mobile |  | 6/11/2019 2:25AM |  | We can put a small indicator at the top of the screen, and when the indicator turns green (new chat content), then the invitees can swipe "right" to see the chat content and then simply swipe left to get back to the collaboration. It would be faster than a toggle and then having to select a Chat Tab.